DEIS Plan

School: Scoil Eoin Naofa

Roll No: 17991N

2022 – 2026

School Context:

Patron: Catholic Bishop of Meath

Chairperson: Ita Kearney

Principal: Declan Claffey

Staff: 4 class teachers, 1 full time and 1 shared SET teacher, 1 full time and 1 part-time SNA’s, 1 secretary, Caretaker/Cleaner.

Pupils: 100 boys and girls from Junior Infants to Sixth class

Parents: Parents Association, Parents on BoM

DEIS Status: DEIS Rural

Our DEIS Philosophy:

This school exists for the pupils. The educational progress and welfare of each child is the over-riding consideration in decisions reached at by our teachers and BoM.

Our Key Values:

We believe in providing a holistic education for our pupils.

Purpose of the Plan:

To bring about improvement in educational and social outcomes for those pupils considered to be under-achieving in educational and social terms due to disadvantage and help them achieve their potential.

|  | Prioritised Area of Concern – Literacy |
| --- | --- |
| Target(s) | - To reduce the percentage of children scoring below the 20% percentile by 3%: 2022 stats show - To develop a whole school approach to handwriting. - To increase the availability of books and texts to children, by providing a new school library. |
| Action(s) | Actions should be taken in a sequenced and coordinated manner each year over the three years of the plan to try and ensure maximum effect and to allow for ongoing review, adaptation and refocusing - Continue use of various initiatives that in place in the school: Reading Recovery, Literacy Lift Off, Catch Up Literacy, Dialogical Reading, Building Bridges, Reciprocal Teaching, Paired Reading, First Steps reading and writing – Year 1. - Offer in-service training where necessary to staff for Literacy initiatives that are taking place in the school – Year 1 (CPD). - Handwriting Without Tears training to be completed by SET teacher – Year 1 (CPD). - Develop a school policy on Handwriting – Year 2 (Leadership). - Set up a school library. Use the Aladdin Library system to catalogue all the books in the school. Have a set time each week where pupils bring back and take out books – Year 3 (Leadership). - Yearly trips to the local library by all classes. During each trip, check that each child has their own library card and takes out books (Wellbeing). - Request new books and return old books twice yearly, with the County Library Service. |
| Monitoring | Targets and actions are monitored as follows: - Classroom level – Class teachers - School Level – In-School Management Team - School Support Plus Level – SET teachers |
| Evaluation | The targets and actions will be evaluated termly at staff meetings. Data from standarised test results will be used, along with teacher observations. |
| Review | Yearly review to take place every September. Targets and actions achieved and ongoing are noted. Targets and actions not achieved are assessed as to how best to achieve them and adjusted where necessary. |

|  | Prioritised Area of Concern - Numeracy |
| --- | --- |
| Target(s) | - To develop a whole school approach to Word Problems by June 2026. - To reduce the percentage of children scoring below the 20% percentile by 3%: 2022 stats show - To increase the availability of concrete resources for Maths lessons. |
| Action(s) | Actions should be taken in a sequenced and coordinated manner each year over the three years of the plan to try and ensure maximum effect and to allow for ongoing review, adaptation and refocusing - Complete a stock take of all Maths related resources in the school by June 2023 – Year 1 (Leadership) - Identify new resources needed for Maths and ask the Parents Association to help fundraise for these in September 2023 – Year 1. - Chat and survey with students, at end of 4th class or beginning of 5th class, to identify areas in maths which they find difficult and identify what ways they learn best – Year 1. - Choose an area in the school where Maths resources can be easily accessed by all staff as needed – Year 2. - To update the school policy on Maths, with particular reference to Word Problems – Year 2 (Leadership). - Write up a list of commonly used Maths words – Year 3. - Take part in Maths Week yearly to increase enjoyment of Maths (Wellbeing) - Investigate possible in-service training for staff in Maths – Year 3 (CPD) |
| Monitoring | Targets and actions are monitored as follows: - Classroom level – Class teachers - School Level – In-School Management Team - School Support Plus Level – SET teachers |
| Evaluation | The targets and actions will be evaluated termly at staff meetings. Data from standarised test results will be used, along with teacher observations. |
| Review | Yearly review to take place every September. Targets and actions achieved and ongoing are noted. Targets and actions not achieved are assessed as to how best to achieve them and adjusted where necessary. |

|  | Prioritised Area of Concern - Retention |
| --- | --- |
| Target(s) | - To increase positive attitude towards school in parents and students by 5% year on year, on attitude surveys. - To be a point of contact for pupils and parents and to encourage communication between parties - To support pupils in identifying their personal strengths in order to pick subjects which will allow them to achieve and master skills |
| Action(s) | Actions should be taken in a sequenced and coordinated manner each year over the three years of the plan to try and ensure maximum effect and to allow for ongoing review, adaptation and refocusing - Work with school liaison teachers in secondary schools re subject choices, activities, children with additional needs – Year 1 - Familiarise ourselves with subjects and activities available in the secondary schools – Year 1 - Ascertain what assistive technology is available to students and what pupil support is available – Year 1 - Administer VIA institute personal strengths test and Attitude to School survey yearly – Year 2 (Wellbeing) - Give survey to parents and students who left school in the previous June, “What I wish I knew before secondary school” – Year 2 (Wellbeing) - Use the findings in the surveys to identify concerns for parents and pupils – Year 3 - Have a few past pupils who are still in secondary school speak to 6th class to chat about secondary school – Year 3 (Leadership) |
| Monitoring | - Surveys - SET: transition to Sec school programmes - Feedback from Sec school liaison teacher |
| Evaluation | Evaluated and record mindset changes in parents and pupils |
| Review | Yearly review to take place every September. Targets and actions achieved and ongoing are noted. Targets and actions not achieved are assessed as to how best to achieve them and adjusted where necessary. |

|  | Prioritised Area of Concern - Attendance |
| --- | --- |
| Target(s) | - Improve attendance with those who are absent without reason or explanation - Improve tardiness |
| Action(s) | Actions should be taken in a sequenced and coordinated manner each year over the three years of the plan to try and ensure maximum effect and to allow for ongoing review, adaptation and refocusing - Meet parents of new junior infant students and communicate the importance of attendance and punctuality – Year 1 - Monitor attendance and late arrival on Aladdin – Year 2 - Award certs for those who attend school for 20/30/40 consecutive days – Year 2 (Wellbeing) - Communicate with parents when children’s attendance has improved – Year 3 |
| Monitoring | - Classroom level- class teachers - School Level- In school management team |
| Evaluation | The targets and actions will be evaluated termly at staff meetings and if necessary, in between meetings. |
| Review | Yearly review to take place every September. Targets and actions achieved and ongoing are noted. Targets and actions not achieved are assessed as to how best to achieve them and adjusted where necessary. |

|  | Prioritised Area of Concern - Transitions |
| --- | --- |
| Target(s) | Pre-school – Primary. Primary-Post Primary. 1. To support parents and children through the difficult phase of transfer from primary school to post-primary school. 2. To support parents and children through the difficult phase of transfer from preschool to primary school. 3. To build links between the preschools and the primary school to aid the transition process. 4. To build links between the primary and post primary school to aid the transition process. |
| Action(s) | Actions should be taken in a sequenced and coordinated manner each year over the three years of the plan to try and ensure maximum effect and to allow for ongoing review, adaptation and refocusing Incoming Junior Infants – once enrolled: • Introduction meeting with Junior Infant teacher to support school start – Year 1 • Incoming junior infant welcome pack provided to each family– Year 1 - Transition booklet -Mo Scéal – Year 2 - Class teacher go down to the pre-school to meet the children in the pre-school setting – Year 3 - Ask NEPS psychologist / OT/ Speech and Language therapist etc to be present for open day for infants – Year 3 Outgoing 6th class: • Information on local secondary schools open nights and data (size, location, website) provided to families – Year 1 • Every child to secure a place in secondary school by the end of the enrolment period – Year 1 • Families encouraged and supported through the application process – Year 1 • Visits from secondary schools & past pupils – Year 2 • 6th class transition programme rolled out in 3rd term; class work to support the transition also – Year 2 • Handover phone call /meeting and passports discussed with secondary schools to support transition– Year 1 • Contact SEN and SCP teams in secondary schools for any target students – Year 1 • Have someone from National Parents Council to come to a meeting for 6th class parents before children go to sec school – Year 3 New pupils to the school: • Create welcome pack for new arrivals to the school similar to the Junior Infant welcome pack – school information provided – Year 1 • Parents contacted before arrival of the new pupil to support with uniforms, books, reports from past schools, etc. – Year 1 • Parents and pupil may arrange to meet with the principal/class teacher before attending a full day’s school to familiarise the child with the new environment – Year 1 Transition from class to class. - Developing system for logging of meetings with parents/ other services regarding pupils – Year 3 |
| Monitoring | - 6th class monitoring: September (information), October (application), November (acceptance), March onward (transition programmes for 6th class.). Annual meeting with Principal, 6th class teachers to monitor each September and review for year. - Junior infant monitoring: April (Mo Scéal handed out to incoming students), June (Mo Scéal collected), September (Welcome packs distributed), October (meetings with preschools for incoming JIs), November/December/January (meeting with parents) Junior infant teachers, and Principal in regular contact re junior infants from September to October break. Review meeting in March/April. |
| Evaluation | - Successful transition of all pupils from preschool to primary school - Successful transition of all 6th class pupils from primary school to secondary school. - Collection of transition booklets from prospective and outgoing students. - Creation of welcome packs for students transferring from other schools. - Creation of meeting logging system. |
| Review | Yearly review to take place every September. Targets and actions achieved and ongoing are noted. Targets and actions not achieved are assessed as to how best to achieve them and adjusted where necessary. |

|  | Prioritised Area of Concern – Partnerships with Parents and Others |
| --- | --- |
| Target(s) | - To maximise supports available to alleviate the effects of disadvantage for the children, by building partnerships and linking families to services - To maintain and strengthen current links with local voluntary and statutory agencies. - To actively promote partnership of school with local community organisations: Tidy Towns, G.A.A. Mens Shed, Youth Group. |
| Action(s) | Actions should be taken in a sequenced and coordinated manner each year over the three years of the plan to try and ensure maximum effect and to allow for ongoing review, adaptation and refocusing - Use website, school newsletter, letters to parents or guardians and local newspaper to publicise school activities, accomplishments, policies and events – Year 1 (Leadership) - Develop partnerships with local educational links – Ballymore Pre-school, Moate Community College, Mercy Secondary School, Ballymahon Vocational School, T.U.I. Athlone, Longford Westmeath ETB – Year 2 - Create a Notice Wall in Lobby area, for displaying pupils work and information relevant for parents/ visitors to school – Year 3 - Increased partnership with outside agencies and Child Support Services to improve student outcomes, as well as parent outcomes: Longford Westmeath ETB, Tusla, CAMHS, Triple P, SENO, S&L, OT, NEPS (CPD) - Develop/Foster stronger links with the parents’ association, encourage their involvement in fundraising and school events – Year 1 - Develop partnerships with local community groups: Youth Club, Tidy Towns, Ballymore G.A.A. – Year 2 (Wellbeing) |
| Monitoring | - Track meetings with parents and referrals to outside agencies - Log the number of events and meetings organised with outside agencies - School to keep in touch with parents referred to various services and agencies - Feedback will be sought from teachers, students and parents annually to termly progress |
| Evaluation | - An increase in the number of families linked with the appropriate services shows progression in this area and will be monitored annually. - An increase in the number of parents attending courses provided by the school. - School website to be updated more frequently. - Ensure all staff have access to their school email account and are proficient users of Microsoft suite. |
| Review | Yearly review to take place every September. Targets and actions achieved and ongoing are noted. Targets and actions not achieved are assessed as to how best to achieve them and adjusted where necessary. |